## Sprint Task Allocation
Sr.No | Epic | Feature | Story | Story Points | Task | Assignee | Planned Hours | Planned Days | Start Date | End Date | Task Status
1 | MPDA-MRT: Member Retention Model Analytics: Tactical | MPDA-MRT: 6.1 - Data Source & Consumption Readiness | Data Source & Consumption Readiness | 8 | Review approved consumption data contract and source requirements | Keerthi | 8 |  | 22-Sep | 23-Sep | In Progress
2 |  |  |  |  | Identify required Databricks consumption tables/views/outputs | Tavneet | 8 |  | 22-Sep | 23-Sep | In Progress
3 |  |  |  |  | Perform source-to-requirement gap analysis | Keerthi | 8 |  | 24-Sep | 24-Sep | Planned
4 |  |  |  |  | Validate required fields for customer, segment, risk and outcome reporting | Keerthi | 8 |  | 24-Sep | 25-Sep | Planned
5 |  |  |  |  | Validate data availability and refresh frequency | Tavneet | 8 |  | 24-Sep | 25-Sep | Planned
6 |  |  |  |  | Confirm source data quality and completeness | Tavneet | 8 |  | 25-Sep | 26-Sep | Planned
7 |  |  |  |  | Document data source mapping and assumptions | Keerthi | 8 |  | 26-Sep | 26-Sep | Planned
8 |  |  |  |  | Obtain confirmation on the approved consumption source | Tavneet | 8 |  | 29-Sep | 29-Sep | Planned
9 |  |  |  |  | Identify data source mapping | Keerthi | 8 |  | 29-Sep | 30-Sep | Planned
10 |  |  |  |  | Review consumption data | Tavneet | 8 |  | 30-Sep | 30-Sep | Planned
11 |  | RADM: Report Wireframes and Storyboards - Part B | RADM: Report Wireframes and Storyboards - Part B | 8 | Changes in Behavioral Dashboard Mockup | Keerthi | 8 |  | 22-Sep | 23-Sep | In Progress
12 |  |  |  |  | Changes in Retention Executive Summary Mockup | Tavneet | 8 |  | 22-Sep | 23-Sep | In Progress
13 |  |  |  |  | Changes in Rollover Dashboard Mockup | Keerthi | 8 |  | 24-Sep | 25-Sep | Planned
14 |  |  |  |  | Getting Sign Off on the Power BI Dashboard - Part B | Tavneet | 8 |  | 26-Sep | 29-Sep | Planned
15 |  |  |  |  | Review - Changes in Retention Executive Summary Mockup | Keerthi | 8 |  | 30-Sep | 30-Sep | Planned
Total Story Points
Story-Level Summary – Story Points Remain at Story Level
Story | Story Points | Keerthi Hours | Tavneet Hours | Total Hours | Total Days | Allocation
Data Source & Consumption Readiness | 8 |  |  |  |  | Both
RADM: Report Wireframes and Storyboards - Part B | 8 |  |  |  |  | Both
TOTAL | [5 empty] | Both
10-Day Sprint Capacity – 2 People | [6 empty] | How to use this sheet: • Story 1 = 8 Story Points. • Story 2 = 8 Story Points. • Both stories can be worked on by both team members. • Story Points remain at Story level; they are not split between people. • Total sprint commitment = 16 Story Points. • Tasks are used to track the actual person doing the work and planned hours/days. • 10 sprint days = 8 delivery days + 2 meeting/ceremony days per person. • Task-level time allocation is separate from Story Points.
Assignee | Sprint Days | Meeting/Ceremony Days | Delivery Days | Allocated Task Hours | Capacity Check
Keerthi | 10 | 2 | 8
Tavneet | 10 | 2 | 8
TOTAL

## How to Use
Level | Planning Rule
Epic | Keep the overall MPDA-MRT initiative.
Feature | Keep the functional area such as Data Source & Consumption Readiness or RADM.
Story | Story gets the Story Points. Story 1 = 5 and Story 2 = 3, total = 8.
Task | Story gets the Story Points. Story 1 = 8 and Story 2 = 8, giving a total sprint commitment of 16 Story Points.
Time | Track planned hours/days at task level. This shows individual workload without changing Story Points.
Sprint Capacity | Each person has 10 sprint days, with 8 delivery days and 2 days for meetings/ceremonies.