## Additional Stories
Epic | Story | Description | Acceptance Criteria | Tasks | Tags/Fields
Data Discovery & Source Analysis | Analyze source systems and data domains | Review SonataODS Bronze, Silver, Gold layers and Salesforce objects. | Source inventory completed; key tables documented; business owners identified. | Analyze Bronze/Silver/Gold tables; Analyze Salesforce objects; Create source-to-report mapping. | Data Discovery, Analysis, 3-5d
Data Quality & Reconciliation | Data quality framework | Define validation rules and reconciliation process. | Validation checklist created; reconciliation completed. | Validate record counts; KPI calculations; member counts; FUM calculations; reconciliation report. | Data Quality, Validation, 3-5d
Semantic Model Design | Build semantic model and business measures | Design reusable Power BI semantic layer. | Star schema finalized; measures documented. | Create dimensions, facts, date table, DAX measures, business validation. | Data Model, DAX, 4-7d
Security | Implement Row Level Security (RLS) | Restrict report access based on user roles. | Users only see authorized data; security testing completed. | Define security matrix; implement RLS; test access. | Security, RLS, 2-4d
Refresh & Gateway | Configure refresh strategy | Configure dataset refreshes and gateway connectivity. | Refresh completes successfully; monitoring established. | Configure gateway; incremental refresh; schedules; failure testing. | Gateway, Refresh, 2-3d
Business KPI Governance | Define KPI catalogue | Create agreed business definitions for KPIs. | KPI document approved; business sign-off received. | Define Retention Rate, FUM, Member Growth, Attrition Metrics. | Business Analysis, KPI, 2-3d
AI Assisted Development | AI-assisted development and documentation | Use Copilot/LenAI for optimization and documentation. | AI outputs reviewed; productivity improvements documented. | DAX optimization; documentation generation; AI recommendations review. | AI-Assisted, Copilot, LenAI, 1-2d
Release Readiness | Production readiness assessment | Ensure solution is ready for production deployment. | Checklist completed; sign-offs obtained. | Performance, security, documentation, deployment review. | Release, Governance, 1-2d